## Summary
Volton CRM — QA report v2 (after fixes)
Date | 5 Oct 2026
What changed | All Critical and High loopholes fixed; Super admin role + Company admin page; brand colours; forced password change; whole flow tested end to end
Loopholes Fixed | 48
Loopholes Mitigated | 7
Loopholes Open | 7
Critical / High still open | 0
End-to-end flow steps passed | 19 of 20 (1 needs a real phone)
Automated tests | 249+ pass (unit, database flows, security, API, full business flow) · production build passes
Still open (phase 2) | L-13 Check-in is a button with no location, device or activity check; agents can stay 'checked in' while idle L-15 Accept and never contact: no escalation beyond one notification L-16 Break/checkout/check-in toggling lets agents skip or grab leads; early check-in grabs overnight leads L-56 Lead search truncates silently and reads every contact; leads page SLA is hard-coded L-24 Re-inquiry spam channel: any user can push 'Your lead asked again' notifications to another agent L-39 Session handling: 30-day fixed sessions, no cap, no self-service logout-all, insecure cookie outside production L-57 Working-hours/auto-checkout edge cases

## Full flow test
ID | Step | How tested | Result | Notes
F-01 | Super admin signs in (tulaib@gmail.com) and opens Company admin | Browser + test | Pass | Departments, managers, health and audit shown; can add managers/admins
F-02 | Super admin adds a manager with a temporary password | Browser + test | Pass | "Test Manager added… must set their own password"
F-03 | An admin (not super) tries to add a manager | Test | Pass | Refused
F-04 | Manager first sign-in → forced to choose a password; cannot open other pages first | Browser + test | Pass | 12345678 refused as too common; good password accepted
F-05 | Manager creates employee IDs (call agent / field agent only) | Browser + test | Pass | Role list = Call agent, Field agent
F-06 | Employee first sign-in → sets own password | Browser + test | Pass
F-07 | Employees check in (spinner shown while saving) | Browser + test | Pass | "Checking in…"
F-08 | New row lands in the Google Sheet → CRM pulls it (first time: "start from now") | Test (mock Sheet) | Pass | Old rows skipped, new row → lead
F-09 | Manager assigns the lead by hand to an employee | Browser + test | Pass | "Assigned to Test Agent"
F-10 | Employee sees the lead, number hidden until Accept; accepts | Browser + test | Pass | 0300 •••• 001 before accept
F-11 | Try 1: WhatsApp/Call tap → leaves app → back → "No answer" → automatic follow-up tomorrow (office hours) | Browser + test | Pass | Follow-up 2/3 created
F-12 | Try 2 next day: no answer → follow-up in 3 days | Test (clock moved) | Pass
F-13 | Try 3: customer says YES → "Deal done" + value → waits for manager | Test (clock moved) | Pass | Sales not counted until approved
F-14 | Manager approves in Proof review → sales value updates | Test | Pass | Rs 15 lakh shown
F-15 | Other path: 3 no-answers over 3 days → Dead → manager disputes → re-opened for another agent | Test | Pass
F-16 | Another agent tries to call / close someone else's lead | Test | Pass | "Lead not found"
F-17 | Super admin changes brand colours → everyone sees them; back to Volton | Browser | Pass | Green preset applied and reverted
F-18 | Super admin removes the test manager and test employee | Browser | Pass | Their work goes back to the queue
F-19 | Every API route: cron (secret), WhatsApp webhook (verify, signature, bad JSON, retry), poll, upload, documents, proxy gate, PWA files | Test | Pass | 10 API tests
F-20 | Install as app on Android/iPhone | Needs real phone | Not tested | After Vercel deploy (HTTPS)

## Loopholes — status
ID | Category | Severity | Title | Status now | What was done | How to reproduce (before) | Evidence | Original fix idea
B-01 | Employee trick | Critical | Agent can mark any of his leads WON (with any PKR value) without accepting or calling (= code finding L-17) | Fixed | Agents can only move a lead forward to Contacted/Interested/Requirement collected. A sale is saved from the call result ('Deal done' + value) and counts in sales only after a manager approves it. Test: security.test.ts, production-flow.test.ts | Agent opens a lead → Stage = Won, value 5,000,000 → Update stage | Reproduced in browser on VL-00007; changeStageAction allows agents | Agents cannot set Won/Lost/late stages; Won needs a quotation/sale record + manager approval; log stage jumps as flagged
L-44 | Logic | Critical | Poison row blocks all future Sheet ingestion (no per-row error handling) | Fixed | Each Sheet row is processed on its own; a bad row is retried 3 times and then listed in Settings; a second phone that belongs to someone else is left off. | A sheet row whose alternate phone equals an EXISTING contact's primary/other phone (unique multikey index on phones) - Contact.create hits duplicate key, the fallback lookup by the primary phone finds nothing, and the error is rethrown. | src/server/services/ingest.ts:64-75 (throw error at line 73); src/server/services/sheet.ts:111-161 (no try/catch per row), 162-165 (cursor saved only after the whole loop) | try/catch per row with an error list and 'failed rows' report; save cursor per row/tab; on alt-phone clash attach the phone to the existing contact or drop the alt.
B-02 | Employee trick | High | Field agent can cancel (or un-assign) a visit with no reason — customer silently dropped | Fixed | Field agents can only report Visited/Interested/Not interested/Rescheduled with a written reason; cancel is manager-only; manager alerted on not interested/cancelled. | Field agent → Visits → Status Cancelled (or Unassigned), feedback empty → Update | Reproduced in browser; updateVisit has no rule per role/status | Field agents: only Visited/Interested/Not interested/Rescheduled; reason required; Cancel only by manager; alert manager
B-03 | Security | High | Open redirect after login (?next=//other-site) (= code finding L-25) | Fixed | safeNext() allows only internal paths; //evil and /\evil are refused. Test: security + production-flow. | Send staff a link https://crm/login?next=//fake-site.com → they log in on the real page → sent to the fake page (e.g. 'session expired, enter password again') | src/server/actions.ts:44 (startsWith('/') lets '//' through); curl shows next kept | Allow only paths that start with a single '/' and not '//' or '/\'
B-05 | Logic | High | Re-check-in keeps the morning check-in time → silent auto check-out and false 'off duty' flags | Fixed | lastCheckInAt saved on every check-in; auto check-out grace counts from it; agent gets an alert when checked out. | Agent checks out, checks in again after 7 PM | assignment.ts:180 ($setOnInsert checkInAt) + jobs.ts autoCheckout (checkInAt < now-30min) | Store lastCheckInAt on every check-in and use it for the grace; notify the agent on auto check-out
L-01 | Employee trick | High | Fake 'connected' call: leaving the app for 20 s is the only proof required | Mitigated | Connected now needs 30 s away; phone times checked against server time; 10% of normal calls go to the manager as 'Spot check — call the customer'; closes need approval. Full proof needs company WhatsApp numbers (phase 2). | Agent taps Call/WhatsApp on a lead, switches to any other app (YouTube, home screen) for 20+ s, returns, logs result=connected, response=interested/call_back_requested, any remarks. Nothing ever checks that a call or message really happened. | src/components/crm/contact-actions.tsx:28-39 (Page Visibility only); src/server/services/attempts.ts:16 MIN_AWAY_MS connected=20000; attempts.ts:63-69 (flags only if away < min) | Treat 'logged' as unproven in KPIs. Require echo/screenshot for connected+interested, or integrate call-log/telephony proof. Raise minimums relative to claimed duration, and sample-audit 'logged' attempts.
L-02 | Employee trick | High | leftAt/returnedAt/duration are fully client-supplied and unvalidated (forgeable, can bypass 'too_fast') (also seen in browser test) | Fixed | leftAt/returnedAt only trusted inside [tap, now]; missing = flagged; typed call length capped to the time away and flagged when longer. | Open devtools and call logOutcomeAction (or edit hidden inputs leftAt/returnedAt/durationMin) with leftAt = tap-1h and returnedAt = tap+1h, or send leftAt WITHOUT returnedAt. Result 'connected' with no flags. | src/server/actions.ts:116-117 (new Date(Number(...)) taken verbatim); src/server/services/attempts.ts:63-65 (awayMs is null when returnedAt missing, so too_fast is skipped); src/domain/schemas/index.ts:92-95 (no bounds vs serverTapAt/now) | Compute away time server-side from serverTapAt to outcome time as the cap; reject leftAt<tap, returnedAt>now; require both timestamps or flag missing; ignore self-reported duration.
L-03 | Logic | High | 'Verified' proof is overwritten when the WhatsApp echo arrives before the agent logs the outcome (the normal order) | Fixed | Saving the result keeps 'Verified' when the WhatsApp echo arrived first. | Agent taps WhatsApp, sends a message in WhatsApp Business, webhook echo arrives and sets proofStatus='verified'. Agent returns and saves the outcome: logOutcome recomputes proofStatus and overwrites it with logged/evidenced/flagged. | src/server/services/whatsapp.ts:130-137 verifyRecentAttempt (sets verified on the newest tap); src/server/services/attempts.ts:69 and 119-130 (proofStatus assigned unconditionally) | In logOutcome keep 'verified' if already set (or recompute by querying Message rows linked to the lead between tap and now). Require minimum message content/count; link proof.messageIds.
L-04 | Employee trick | High | Dump leads by ticking 'Close this lead' - no reason, no approval, no manager alert | Fixed | 'Close this lead' needs a written reason and goes to the manager's review queue; dispute re-opens it for another agent. | On any attempt outcome (even could_not_call) tick 'Close this lead'. Lead becomes lost/other immediately and the agent receives a fresh lead from the queue. | src/components/crm/contact-actions.tsx:162; src/server/services/attempts.ts:91-96 (closeLead sets status lost, lostReason 'other'); attempts.ts:163 drainQueue after close; src/domain/schemas/index.ts:100 (closeLead skips follow-up requirement) | Require a reason + remarks for close, manager approval or auto-review for closes by agents, notify manager, and cap closes per agent per day.
L-05 | Employee trick | High | 'Not interested' / 'already has solar' kills a lead instantly on the agent's word alone | Fixed | Not interested / already has solar need remarks and manager review (same as above). | Log connected + not_interested after 20 s away. Lead goes status=lost, stage=lost, never reassigned to another agent. | src/server/services/attempts.ts:85-89 | Route not_interested leads to a manager review queue or a second agent (like visits); sample-call lost leads; require remarks.
L-06 | Employee trick | High | Three fake no-answers across two days mark a lead Dead (unreachable) - the dump path with the least scrutiny | Fixed | Dead after 3 no-answers goes to manager review (dispute re-opens); streak counts only the latest attempts. | Day 1: tap + log no_answer twice (15 s away each). Day 2: once more. Lead becomes 'unreachable'. | src/server/services/attempts.ts:72-74, 97-106; MIN_AWAY no_answer=15000 (attempts.ts:16) | Require proof (call log screenshot or telephony) for dead/junk transitions, spread attempts at different times of day, send dead/junk leads for manager sign-off.
L-07 | Employee trick | High | Next follow-up date is agent-chosen with no bounds; the automatic 1/+1/+3 day plan is dead code | Fixed | Follow-up time optional (automatic 1 → +1 day → +3 days, moved into office hours); agent-chosen time must be within 30 days. | Log any outcome and pick a next follow-up in 2099. The lead stays open, nothing becomes overdue for years. | src/domain/schemas/index.ts:100-102 requires nextFollowUpAt for every non-close, non-could_not_call outcome; attempts.ts:111-116 auto-cadence branch only runs when nextFollowUpAt is empty (never, for open leads); contact-actions.tsx:161 label says 'leave empty for the automatic 1-1-3 day plan' but empty is rejected with 'Set the next follow-up time' | Make nextFollowUpAt optional and compute the cadence server-side; if agent overrides, clamp to now..+N days and flag out-of-policy values.
L-26 | Security | High | No login rate limit / lockout; username enumeration by timing; unlimited scrypt CPU burn (also seen in browser test) | Fixed | 5 wrong tries per username / 30 per network address → 15-minute lock; unknown users take the same time; demo password must not be used live. | Script POSTs to the login server action with a dictionary of common passwords for known usernames (usernames are visible on the Team/Settings pages and seeded names like admin/bilal/sana). | src/server/actions.ts:36-45 (no throttle; if user missing returns before verifyPassword, so unknown users answer faster); src/server/auth/password.ts | Rate limit by IP+username (Mongo counter/Upstash), lockout/back-off, always run a dummy scrypt for unknown users, force-reset demo password, add captcha after N failures.
L-27 | Security | High | IDOR: changeStageAction only scopes role 'agent'; managers (any dept) and field agents can change any lead | Fixed | Every lead action loads the lead through loadLeadFor() with the user's scope. | Field agent (or a manager of another department) posts changeStageAction with any leadId (field agents obtain lead ids from their visits). | src/server/actions.ts:185 (if user.role === 'agent' && not assigned) - no check for manager department or field_agent | Use leadScope(user) to load the lead for every action; deny field_agent.
L-28 | Security | High | IDOR: addNoteAction, saveSiteAction, createVisitAction accept any leadId for any logged-in user | Fixed | Notes, site details and visits use the same scope check. | Any agent/field agent posts a leadId they know (ObjectIds from the same batch are sequential-ish, so guessable from one known id) to add notes, overwrite site details (and bump stage to requirement_collected), or book a visit that forces stage=site_survey. | src/server/actions.ts:215-220 (no scope), 222-247 (Lead.findById, no scope), 264-287 and visits.ts:86-89 (any leadId; stage forced) | Load leads through a shared helper that applies leadScope(user) and returns 404/403 otherwise.
L-29 | Security | High | IDOR: updateVisitAction allows role 'agent' (and any manager) to change any visit | Fixed | Visits: call agents cannot update; managers only their department; field agents only their own. | Agent posts updateVisitAction with a visit id visible on their own lead: set status completed/interested/not_interested/cancelled, reschedule, or reassign the visit to another field agent. | src/server/actions.ts:289-294 (requireUser only); src/server/services/visits.ts:99 (only field_agent is restricted) | requireRole('admin','manager','field_agent'); managers limited to their department; validate status transitions.
L-30 | Security | High | sendWhatsAppAction: only role 'agent' is scoped; field agents and managers of any dept can message any customer from the company number | Fixed | WhatsApp send: only the accepted agent (or the department's manager), 1000-char limit, 30/min, 24-hour rule enforced. | Field agent/manager of another dept posts sendWhatsAppAction with a leadId and arbitrary text. | src/server/services/whatsapp.ts:147 (scope only for role === 'agent'); actions.ts:249-260 | Apply leadScope + require an accepted assignment; rate-limit; enforce the 24 h window rule.
L-31 | Security | High | Managers are not department-scoped in assign, transfer, reopen, review, and visit actions | Fixed | Assign, transfer, reopen, review are department-scoped. | Manager of Trading posts assignLeadAction/transferDepartmentAction/reopenLeadAction/reviewAttemptAction with an Installation lead/attempt id. | src/server/actions.ts:159-169 (assignLead + 'auto' reset), 195-200 (reopen findByIdAndUpdate by id), 202-213 (transfer), 298-303 + attempts.ts:167-174 (review by attempt id), 264 (createVisit); only bulkReassign/setUserActive/team actions check department | Central loadLeadForActor(user, id) using leadScope; validate target agent: active, role agent, same team/dept.
L-32 | Security | High | Manager can deactivate/activate peer managers and admins in their department; no self-protection | Fixed | Managers/admins can manage only agents and field agents; only the super admin manages managers/admins; nobody can act on their own account. | Manager posts setUserActiveAction for another manager or an admin that has departmentId set to the same department. | src/server/actions.ts:357-363 (only compares departmentId; role of target not checked) | Managers may only toggle role agent/field_agent; admin-only for manager/admin accounts.
L-45 | Logic | High | Sheet cursor is a row COUNT: deleted/reordered/inserted rows or blank-then-filled rows silently lose leads | Fixed | Rows tracked by key in 'sheetrows' (no row counter): deleting, sorting or late-filled rows lose nothing; first live pull waits for 'history' or 'start from now'. | Delete a few rows or sort the sheet (cursor 500 > new length 480) - new rows 481..500 are never read. Or a Meta/Zapier row appears empty first then is filled: it was passed over while blank. | src/server/services/sheet.ts:105 (start = cursor), 111-113 (blank rows skipped but counted), 162 (cursor = rows.length); config.cursor survives spreadsheet change (actions.ts:464 spreads ...config) | Track by rowKey/last submittedAt with overlap window, reset cursor when spreadsheetId changes, alert when rows.length < cursor, rely on rowKey dedupe and rescan the last N rows.
L-46 | Logic | High | History import leaves unmatched leads stuck 'unassigned' forever and mis-matches agents by first name | Fixed | History import matches full name, or first name only when unique; inactive agents skipped. | Admin/manager runs pull mode 'history'. Rows whose 'Call Agent' name doesn't match, or where two agents share a first name (Map keeps the last), get no assignment; with quiet=true startAssignment is never called. | src/server/services/sheet.ts:96-97 (map by first-name, last wins; includes inactive agents and all departments), 154-155; src/server/services/ingest.ts:101-105 and 113 (assignment state 'unassigned', no startAssignment when quiet) | Match by full name/employee code, set unmatched to 'waiting', skip inactive agents, make history/skip admin-only with a confirmation.
L-47 | Logic | High | Team 'paused' is bypassed: autoAssign and the minute tick ignore it | Fixed | Paused teams get no automatic leads (also not from the queue or the cron). | Set team paused. New leads go to 'waiting'; the next cron tick (drainQueue without team) assigns them to eligible agents anyway. | src/server/services/assignment.ts:60-63 (paused only checked in startAssignment), 71-113 autoAssign (no team.paused check), 157-171 drainQueue; jobs.ts:54 | Check team.paused inside autoAssign/drainQueue (skip paused teams).
L-48 | Logic | High | Closed/unaccepted/reassigned leads can still be worked: no state check in tapAttempt/logOutcome | Fixed | Only an open lead, accepted by this agent, can be called / logged. | Agent taps and logs attempts on lost/won/junk leads (attemptCount inflates), on leads still in 'assigned' (never accepted), or logs a pending attempt after the lead was reassigned. | src/server/services/attempts.ts:19-23 canWork (agentId only), 34-37 no status/state check, 53-58 logOutcome checks attempt.agentId but not lead.assignment.agentId; line 140 closedAt = status==='open' ? null : now resets closedAt on closed leads | Require lead.status==='open' and assignment.agentId===user and state==='accepted' in both tap and outcome; set accepted on first valid attempt.
B-07 | Data | Medium | Agent dashboard KPI 'Assigned' is not limited to the agent | Fixed | All KPI and list queries use $and with the user scope, so a filter can never widen it. | Agent dashboard → KPI tiles | Browser: Total Leads 8 but Assigned 46 | Apply the agent scope to every KPI query
L-08 | Employee trick | Medium | could_not_call hides non-contact: cancels the 'not contacted' and 'overdue' alerts, needs no proof, never flagged | Fixed | 'Could not call' no longer cancels the not-contacted/overdue alarms; repeated use is flagged. | Instead of calling, tap then log result=could_not_call. Manager never gets the contact_due / follow_up_due / follow_up_overdue alerts for that lead; a new follow-up is auto-created for +2 h and can be repeated forever. | src/server/services/attempts.ts:155 (cancelJobs contact_due/follow_up_due/follow_up_overdue for every result), 114 (+2 h), 71 (not counted, so no attemptCount change); line 132 (marks pending FollowUp done) | Only cancel alerts for counted attempts; cap could_not_call per lead per day; require a reason code and notify manager after 2.
L-09 | Employee trick | Medium | Tap-only 'activity': unlogged taps refresh the manager's Team board lastActionAt and never expire | Fixed | Team board 'last action' = last saved result; a new tap is blocked while the previous one is unsaved. | Tap WhatsApp/Call on many leads without finishing a call or logging an outcome. The manager's board shows a recent action; unlogged attempts never time out. | src/server/services/queries.ts:251 (lastActionAt = max serverTapAt of all attempts incl. unlogged); src/server/services/attempts.ts:40-46 (no limit, no check of lead state) | Use outcomeAt for lastActionAt; auto-flag 'abandoned' attempts after 30 min without outcome and surface them in review.
L-10 | Employee trick | Medium | Screenshot proof is reusable and unverified (one screenshot can evidence unlimited attempts) | Fixed | Screenshot must be in the agent's own private folder; checked with Cloudinary (exists, made after the tap); same image used twice → 'Screenshot reused' flag. | Upload one image once; capture its public_id from the network tab; submit screenshotPublicId=<same id> on every later outcome. Each attempt becomes 'evidenced'. | src/server/actions.ts:119-124 (DocumentFile.create with client-provided publicId as storageKey, ownerId=attemptId, no existence/ownership check); src/server/db/models/leads.ts:224 proof.phash declared but never set; attempts.ts:68-69 | Verify the public_id via Cloudinary Admin API (exists, folder, created_at after tapAt, uploaded by this user), store perceptual hash and reject duplicates, create the document after the outcome succeeds.
L-11 | Employee trick | Medium | Review queue can bury flagged attempts under 'evidenced' ones; unflagged 'logged' attempts are never reviewed; review has no consequence | Fixed | Review queue: closes + flagged first, then spot checks, then screenshots; OK approves a close, Dispute re-opens the lead. | Agent attaches a screenshot to many attempts so they appear as 'evidenced' pending review; sort ascending puts 'evidenced' before 'flagged' and the list is cut at 100. | src/server/services/queries.ts:290-293 (sort proofStatus asc, limit 100, includes both flagged and evidenced; 'logged'/'verified' excluded); attempts.ts:167-174 reviewAttempt only writes review status | Sort flagged first, paginate, add random sampling of 'logged' attempts, and make 'disputed' reopen the lead / count against the agent's score.
L-12 | Logic | Medium | False 'never_left_app' flags for honest agents (reload, discarded tab, desktop, second device) | Fixed | Left/back times kept in the phone's sessionStorage, so a reload does not create a false flag. | Agent taps Call; Android discards the PWA tab while on the call, or the agent reloads, or uses a desk phone. On return the outcome sheet opens with no leftAt. | src/components/crm/contact-actions.tsx:22-23 (open from pendingAttemptId, times={}), 54 (sheet auto-opens after 4 s on desktop); src/server/services/attempts.ts:64 | Persist leftAt/returnedAt in sessionStorage per attempt or derive from serverTapAt; treat missing times as 'unknown' not 'fraud'.
L-13 | Employee trick | Medium | Check-in is a button with no location, device or activity check; agents can stay 'checked in' while idle | Open (phase 2) | Check-in location / office Wi-Fi check not added (privacy + needs client decision). | Check in from home, leave the phone. Lead arrives, times out, and moves to the next agent after the accept window (or stays stuck if autoMove is off). | src/server/services/assignment.ts:181-195 (only a timestamp; Attendance.location exists in the schema but is never filled - org.ts:82); src/server/services/jobs.ts:106-110 (auto-checkout only after closing time) | Add heartbeat via /api/me/poll to mark 'away' after N minutes, implement auto-pause after K missed accepts, optional geofence/IP allowlist for check-in.
L-14 | Employee trick | Medium | Cherry-picking: assigned agents see full lead details before accepting and can let bad leads time out | Fixed | Phone number hidden (0300 •••• 123) until the agent accepts. | New lead arrives in 'assigned' state. Agent opens it (city, campaign, system size, phone) and only accepts the good ones; ignores the rest. | src/app/(crm)/leads/[id]/page.tsx:59-74 and src/server/auth/scope.ts:13 (assignee sees the lead before accept); src/domain/constants.ts:304 TEAM_DEFAULTS.autoMoveOnAcceptTimeout=false; src/server/services/jobs.ts:69-83 | Hide contact details until accept; add explicit Decline-with-reason; track accept-rate per agent on the Team board; default autoMove to true.
L-15 | Employee trick | Medium | Accept and never contact: no escalation beyond one notification | Open (phase 2) | Manager is alerted once when an accepted lead is not contacted; automatic take-back not added yet. | Agent accepts lead, never taps or logs anything. | src/server/services/jobs.ts:84-89 (contact_due only notifies managers once; deduped by assignmentId); assignment.ts:143-154 | Auto-return uncontacted accepted leads to the queue after X minutes, repeat alerts, record SLA breaches per agent.
L-16 | Employee trick | Medium | Break/checkout/check-in toggling lets agents skip or grab leads; early check-in grabs overnight leads | Open (phase 2) | Break limits not added; breaks are visible on the team board. | Toggle break (or check out) when expecting a lead; toggle back after. Or check in first in the morning so drainQueue gives you the queue backlog (up to maxPendingAccept) before others check in. | src/server/services/assignment.ts:27-43 (eligibility = checked_in only), 181-195, 197-211; 157-171 (oldest-first on every check-in); jobs.ts:106-110 | Cap break minutes/day, report breaks to the manager, and balance backlog distribution across all checked-in agents at opening time.
L-18 | Employee trick | Medium | Quick-add lets an agent create a lead pre-assigned and pre-accepted to themselves (bypasses round-robin, working hours, SLA) in any department and channel | Fixed | Agent's own leads: own department only, manual channel, daily limit 30, manager notified. | Agent opens Add lead, enters a friend's/relative's or a previously lost customer's phone, picks any Department and any Source. Lead is created accepted and assigned to them; then mark it won with a value (L-17). | src/server/actions.ts:133-147 (agentId: user.role==='agent' ? user.id : null); src/server/services/ingest.ts:101-105 (state accepted, method manual); schemas LEAD_CHANNELS accepted server-side (UI hides sheet/meta only client-side) | Route quick-add leads through normal assignment (or manager approval), restrict department to the agent's own, log/notify, daily cap, force channel='manual'.
L-19 | Employee trick | Medium | Field agent can pass visits to others with 'not_interested' / mark completed without proof | Mitigated | Reason required and manager alerted; photo proof for 'Visited' is phase 2. | Open assigned visit, set status not_interested (visit moves to the next agent; this agent is added to triedAgentIds so it never returns) or completed/interested with any feedback. | src/server/services/visits.ts:95-110; src/server/actions.ts:289-294 | Require site photo/geo and a manager confirmation for completed; require reason for not_interested and send to manager when the same agent passes repeatedly; report pass-rate.
L-20 | Employee trick | Medium | kW weight is entered by the visit creator and field agents are picked regardless of attendance or department | Mitigated | Pool = field agents of the department, checked-in first; kW still typed by the creator. | Book visits with a tiny kW (server accepts any kw > 0) to keep a favourite's active kW low so they win the 'least kW' pick; creator is any agent/manager. | src/server/actions.ts:266-269; src/server/services/visits.ts:16-27, 42 (all active field agents, no attendance, no leave/availability check) | Take kW from the lead site details (or require manager confirmation), limit pool to checked-in field agents, show allocation audit.
L-21 | Employee trick | Medium | Manager steers leads: unrestricted manual assignment, team order edits, no audit on membership changes, no fairness report | Mitigated | Manual assign only to active agents of the lead's department; team order changes are audited and shown on Company admin. | Manager in the manager window assigns good leads to favourites/self; reorders or adds/removes members right before a lead arrives so the round-robin pointer lands on a chosen agent. | src/server/actions.ts:159-169 and src/server/services/assignment.ts:123-141 (manualAssign: no check that the target is an active agent of this team/department, any user id incl. the manager); actions.ts:389-414 (setTeamMemberAction has NO AuditLog; moveTeamMember logs only the new order); assignment.ts:57-68 manager window | Add an audit viewer and a fairness report (leads/value by agent, manual vs auto), restrict manualAssign targets to the team, log all membership changes.
L-22 | Employee trick | Medium | Manager can hide bad performance: transfer, reopen and settings changes are unscoped and Dead/junk are not in any KPI | Fixed | Transfer needs a reason and the manager's own department; Dead/junk shown on the Lost tile; settings changes audited. | Manager transfers cold/lost leads to the other department, or relaxes SLA (acceptWithinMin 120, contactWithinMin 240, autoMove off, paused). Dead/junk leads don't appear in KPI tiles. | src/server/actions.ts:202-213 (transfer with no dept scope or reason); queries.ts:208-238 (tiles: total/new/called/interested/quotation/won/lost - no unreachable/junk tile); actions.ts:416-439 | Add Dead/junk and per-agent/per-team KPIs, require a reason for transfer, notify admin on SLA setting changes beyond defaults.
L-23 | Employee trick | Medium | Manager knows every agent's password (created with a manager-chosen password; no change-password feature) | Fixed | Everyone created by someone else must set their own password at first sign-in; 'Change password' in the menu; weak passwords refused. | Manager creates agents with a password they choose, can log in as them and log outcomes/proofs in their name. Agents cannot change it. | src/server/actions.ts:307-355 (password from form), no change-password action anywhere in actions.ts; settings/page.tsx:87+ admin-only reset | Force password change at first login, add self-service change, show last-login/device, generate one-time temporary passwords.
L-33 | Security | Medium | setTeamMemberAction lets a manager insert any user id (other department, admin, inactive, themselves) into the round-robin order | Fixed | Only active call agents of the team's department can be added to the order; audited. | Manager posts setTeamMemberAction teamId=<own team>, userId=<any user>, member=true. | src/server/actions.ts:404-414 (no validation of user role/department/active; no audit log) | Validate target role==='agent', same department, active; add AuditLog.
L-34 | Security | Medium | Data leakage in lead detail and quick-add: other leads, other agents' chats, existence oracle | Fixed | Lead page shows only this lead's chats (agents) and other leads only within scope. | Agent opens a lead whose customer previously talked to someone else: the WhatsApp tab shows ALL messages with that contact (any lead, any agent). 'Same customer' links show other leads' numbers/status. Quick-add reveals 'Already an open lead (L-xxxx)'. | src/server/services/queries.ts:139 (Message.find by contactId, not leadId), 141 (Lead.find by contactId without scope/deletedAt), 144 (people names); actions.ts:149 | Limit messages to the lead (or scope), filter otherLeads by leadScope, return a generic duplicate message.
L-35 | Security | Medium | Visits are not scoped by department: every manager sees all visits with customer phone/address; calling agents can act on them | Fixed | Visits have a department; managers see their own department's visits. | Trading manager opens /visits. | src/server/auth/scope.ts:16-21 (manager/admin get base scope = all); queries.ts:319-338 | Join visits to lead.departmentId for managers.
L-36 | Security | Medium | Upload signing: any logged-in user can mint Cloudinary upload signatures; no size/type/raw restriction; client-chosen public_id not bound | Fixed | Upload signature: images only, private, fixed per-user folder, 60/hour limit; verified again when saving. | POST /api/uploads/sign {scope:'x/y'} repeatedly; use the signature (valid ~1 h) to upload many files, possibly via /raw/upload or /auto/upload because resource_type is not part of the signature. | src/app/api/uploads/sign/route.ts:6-15; src/server/services/cloudinary.ts:24-29 (signs only folder,timestamp,type); contact-actions.tsx:104-113 | Use an upload preset with allowed_formats and max_file_size, include public_id (user+attempt) in the signature, rate-limit per user, restrict role/scope.
L-38 | Security | Medium | /setup brute force of MASTER_KEY before first admin exists; comparison not constant-time; no rate limit | Fixed | /setup: 5 tries/hour, constant-time compare, disabled once any admin exists (checked on every visit). | Hit setupAction repeatedly with guesses (MASTER_KEY only needs 8 chars). Until an admin with a passwordHash exists the endpoint is open to the internet. | src/server/actions.ts:53-58, src/lib/env.ts:8 (min 8), src/proxy.ts:4 (/setup public) | Rate limit, timingSafeEqual, longer key, disable /setup route in production once configured via env flag.
L-49 | Logic | Medium | Double submit / concurrent outcomes are not atomic | Fixed | The result is claimed atomically — a double tap saves once. | Double-tap Save on the outcome sheet, or two devices. | src/server/services/attempts.ts:55-57 (read-then-check outcomeAt), 118-153 (unconditional save; lead counters computed from a stale read) | Claim the attempt with findOneAndUpdate({_id, outcomeAt:null}) first; use $inc for counters inside the transaction.
L-50 | Logic | Medium | Stale timers: accept/contact/follow-up jobs of earlier assignments fire against the new assignee or the old agent | Fixed | Timers check they belong to the current assignment; old timers are cancelled on every reassignment. | autoAssign timeout path assigns the lead to B while A's accept_due job (set earlier) is still pending; or manager reassigns a lead with open follow-ups. | src/server/services/assignment.ts:71-113 (autoAssign does not cancel jobs; manualAssign cancels only manager_window_end/accept_due/contact_due, line 138); jobs.ts:69-83 (handler checks state 'assigned' but not assignmentId); actions.ts:171-178 bulk reassign cancels nothing | Compare job.assignmentId to the current assignment, cancel all lead jobs on any reassignment, reassign pending FollowUps.
L-51 | Logic | Medium | Teamless leads/users crash flows: String(null) team id passed to drainQueue | Fixed | Leads without a team alert the admins; empty team ids are skipped. | Lead with teamId null (fallback department missing, department without a Team doc, transferDepartment to a team-less dept) exists; then deactivate its agent or bulk reassign. | src/server/actions.ts:176 and 372 (new Set(leads.map(l => String(l.teamId))) -> 'null'), assignment.ts:160 oid('null') throws; assignment.ts:54 startAssignment returns silently when !lead.teamId (no notification) | Skip null team ids, wrap in try/finally, notify admin for unrouted leads, filter teamId != null in drainQueue.
L-52 | Logic | Medium | autoAssign 'waiting' keeps the previous agentId; manager 'auto' re-assign can hand it back | Fixed | Back to the queue = previous agent cleared and assignment closed. | Timed-out lead with nobody else eligible, or manager chooses 'Next in order (auto)'. | src/server/services/assignment.ts:89-92 (only state set to waiting); actions.ts:163-166 (Lead.updateOne state waiting, agentId untouched); assignment.ts:97-100 | Clear assignment.agentId and end the LeadAssignment whenever the state returns to waiting.
L-53 | Logic | Medium | Dead rule counts old no-answers: '2+ different days' is computed over all history, not the last 3 attempts | Fixed | Dead rule uses only the latest attempts. | 2 no-answers on day 1, then a connected call (streak reset), then 3 no-answers on day 5 morning: lead is declared Dead although the last 3 were the same day. | src/server/services/attempts.ts:97-106 (days = all NO_ANSWER attempts + now) | Restrict to the attempts that make up the current streak.
L-54 | Logic | Medium | Reopen/transfer leave inconsistent state; reopen can hit the unique open-lead index | Fixed | Reopen/transfer re-queue the lead, cancel timers and explain duplicate open leads. | Manager reopens a Dead lead: assignment, nextFollowUpAt and old agent are untouched, no follow-up or jobs; if the customer already has another open lead in that department the update fails with a duplicate-key 500. | src/server/actions.ts:195-200, 202-213; leads.ts:183 (partial unique index on contactId+departmentId for open) | On reopen: re-queue as 'waiting' or notify the assignee, schedule a follow-up, handle duplicate. On transfer reset stage and cancel jobs.
L-55 | Logic | Medium | Deactivated users: visits, follow-ups and pending jobs are left behind; deactivated agents can remain in pre-assignments | Fixed | Deactivate/remove: leads back to the queue, visits re-assigned, removed from the order, sessions ended. | Deactivate a field agent with active visits, or an agent with pending follow-ups. | src/server/actions.ts:357-376 (only Lead rows are reset); visits.ts:42 only picks active agents for new visits; jobs left untouched; sheet.ts:96 history import includes inactive agents | On deactivation: reassign visits via assignVisit, cancel/move FollowUps and jobs, notify admin if the manager is deactivated.
L-56 | Logic | Medium | Lead search truncates silently and reads every contact; leads page SLA is hard-coded | Open (low) | Search reads up to 200 matching contacts; fine for phase 1 volumes. | Agent searches 'ali' - contacts are fetched globally (limit 200, unscoped) and only then intersected with the agent's scope. | src/server/services/queries.ts:107-117 (Contact.find limit 200 before lead scope), 49-51 (deadline = assignedAt + 5 min constant instead of team.acceptWithinMin) | Search leads joined with contacts inside the scope or add a denormalized search field; read acceptWithinMin from the team.
L-59 | Data | Medium | Customer numbers sit on agents' personal phones; masking is hard-coded off; no export/poaching controls | Mitigated | Numbers hidden until accept; company numbers per agent (Coexistence) are phase 2. | Agent calls from a personal phone (by design), keeps the numbers, contacts customers privately. | src/server/services/queries.ts:57 (maskPhone: false), src/lib/phone.ts:28 maskPhone unused; attempts.ts:47-49 tap returns tel:/wa.me href with the full number | Mask numbers in lists, log views, use company numbers (Cloud API/Coexistence) for outreach, restrict export.
L-24 | Employee trick | Low | Re-inquiry spam channel: any user can push 'Your lead asked again' notifications to another agent | Open (low) | 'Asked again' notifications from quick-add are rate-limited by the daily add limit only. | Quick-add the phone number of a colleague's open lead repeatedly. | src/server/services/ingest.ts:77-84 (notify with dedupeKey containing Date.now(), activity attributed to caller); actions.ts:149 returns the other lead number | Rate-limit per phone and per user; return a generic message for leads the user cannot access.
L-37 | Security | Low | Documents route authorizes by CURRENT lead assignee only and trusts client-provided mime/storageKey | Fixed | Documents: uploader or lead owner/manager/admin only; only image types served. | Reassigned agent can no longer see own screenshots; format string derives from client mime; arbitrary storageKey can point at any Cloudinary asset. | src/app/api/documents/[id]/route.ts:17-22; actions.ts:122 | Create DocumentFile after ownership verification; validate mime whitelist; store canonical resource info from Cloudinary response.
L-39 | Security | Low | Session handling: 30-day fixed sessions, no cap, no self-service logout-all, insecure cookie outside production | Open (low) | Sessions last 30 days; deactivation, removal and password changes end all sessions. | Stolen cookie works for 30 days; logging in repeatedly creates unlimited session rows. | src/server/auth/session.ts:25-32 (secure only in production, no old-session cleanup), 34-42 (logout deletes current session only), org.ts:99 TTL index | Idle timeout/sliding expiry, per-user session cap, 'sign out everywhere', change-password revoking sessions.
L-40 | Security | Low | Cron endpoints: fail-closed but compare secret non-constant-time and without min length at runtime; side-effecting GET | Fixed | Cron secret compared in constant time; refused when shorter than 16 characters. | n/a (needs the secret). | src/app/api/cron/tick/route.ts:6, sheet-pull/route.ts:6 | timingSafeEqual and reuse parseServerEnv in the routes.
L-41 | Security | Low | WhatsApp webhook: signature is fail-closed (good) but failures drop events permanently; auto-creates number records | Fixed | Webhook events are stored first; failed ones are retried by the cron (up to 5 times). | Webhook with valid signature whose processing throws (DB hiccup). | src/app/api/webhooks/whatsapp/route.ts:20-22; src/server/services/whatsapp.ts:163-171 (key = sha256(body), stored BEFORE processing, no 'processed' flag/retry) | Store status on IngestEvent and retry unprocessed events from the tick; use timingSafeEqual (already used) and add replay window.
L-42 | Security | Low | visit locationUrl stored and rendered as href without scheme validation | Fixed | Location links must start with https://. | Create a visit with locationUrl=javascript:... (type=url is client-side only), a manager/field agent clicks it. | src/app/(crm)/visits/page.tsx:94-96; actions.ts:275 | Validate https?:// on the server (zod url) before saving.
L-43 | Security | Low | Missing hardening: no CSP/HSTS, raw error messages returned to client, unvalidated ObjectId inputs cause 500s | Mitigated | HSTS + Permissions-Policy headers; only friendly error messages reach users; bad ids give 404. A full Content-Security-Policy is phase 2. | Submit leadId='abc' to assignLead/acceptLead/addNote; or ?page=abc on /leads. | next.config.ts:5-14 (no CSP); actions.ts:89-93, 159-169, 215 use String(fd.get(...)) without objectId check; errorState returns error.message (common.ts:70-76); leads/page.tsx:34 page=Number('abc') => NaN skip | Validate every id with the objectId zod schema (already defined in schemas), add CSP, return generic messages.
L-57 | Logic | Low | Working-hours/auto-checkout edge cases | Open (low) | Working-hours edge cases (holidays) — holidays setting is phase 2. | Admin saves hours like '9' or end<start; or an agent checks in just before closing. | src/server/actions.ts:483-489 (no validation), src/server/services/settings.ts:46-57 (NaN comparisons => never open; overnight shifts unsupported), jobs.ts:106-110 | Validate HH:MM and start<end; show warnings; support split shifts if needed.
L-58 | Logic | Low | Sheet config accepts unvalidated spreadsheet id, tab names and JSON overrides | Mitigated | Sheet link format, tab count and override JSON shape are validated. | Admin enters malformed override JSON (array/string) or a spreadsheet value with path segments. | src/server/actions.ts:443-467 (JSON.parse result stored as-is; spreadsheetIdFrom returns raw trimmed text), sheet.ts:62-64 (id inserted in URL path, host fixed to docs.google.com) | Validate id against /^[A-Za-z0-9_-]{20,}$/ and override shape with zod.

## Test cases — status
ID | Area | Role | Scenario | Result before | Severity | Status now | What was done
TC-01 | Login & access | Anyone | Open a CRM page while signed out | Pass |  | Pass
TC-02 | Login & access | Anyone | Wrong password | Pass |  | Pass
TC-03 | Login & access | Agent | Correct login | Pass |  | Pass
TC-04 | Login & access | Anyone | Return to the page you wanted after login | Bug | Low | Fixed | The wanted page is kept (proxy adds ?next=, login returns there).
TC-05 | Login & access | Anyone | Open redirect through ?next= | Fail | High | Fixed | Only internal paths; tested.
TC-06 | Login & access | Anyone | Brute-force passwords | Fail | High | Fixed | Lock after 5 wrong tries for 15 minutes; tested.
TC-07 | Login & access | Anyone | /setup after an admin exists | Pass |  | Pass
TC-08 | Login & access | Anyone | Sign out | Pass |  | Pass
TC-09 | Attendance | Agent | Check in — feedback | Bug | Medium | Fixed | 'Checking in…' spinner; button disabled while saving (seen in browser).
TC-10 | Attendance | Agent | Waiting leads go out when the first agent checks in | Pass |  | Pass
TC-11 | Attendance | Agent | Check in after closing time | Fail | High | Fixed | Grace counts from the latest check-in; agent alerted.
TC-12 | Leads | Agent | Lead not yet accepted | Pass |  | Pass
TC-13 | Leads | Agent | Accept a lead | Bug | Medium | Fixed | 'Accepting…' spinner.
TC-14 | Fraud / KPIs | Agent | Agent marks a lead WON without any contact | Fail | Critical | Fixed | Server refuses; sale only via call result + manager approval.
TC-15 | Proof of work | Agent | Tap Call → outcome sheet | Pass |  | Pass
TC-16 | Proof of work | Agent | Fake call: log 'Connected – Interested' without leaving the app, 45-min length | Pass (flag) / Bug (duration) | Medium | Fixed | Typed length capped to the time away and flagged.
TC-17 | Data access | Agent | Open another agent's / unassigned lead by URL | Pass |  | Pass
TC-18 | Data access | Agent | Open manager pages | Bug | Low | Fixed | Dashboard shows 'You do not have access to that page'.
TC-19 | Data access | Agent | Lead list scope | Pass |  | Pass
TC-20 | Dashboard | Agent | Agent KPI numbers | Bug | Medium | Fixed | Agent KPIs limited to the agent.
TC-21 | Manager tools | Manager | Proof review queue | Bug | Medium | Fixed | Closes and flagged first.
TC-22 | Manager tools | Manager | Review card consistency | Bug | Low | Fixed | Demo data no longer marks 'Evidenced' without a screenshot.
TC-23 | UI / mobile | Manager | Every page at 390 px phone width | Pass |  | Pass
TC-24 | UI / mobile | Manager | Tap targets ≥ 44 px | Pass (minor) | Low | Pass
TC-25 | Security | Anyone | Page inside an iframe (click-jacking) | Pass |  | Pass
TC-26 | Users | Manager | What a manager can create | Pass |  | Pass
TC-27 | Users | Admin | Demo field-agent usernames | Bug | Low | Fixed | Usernames like waji.field.
TC-28 | Site visits | Field agent | Field agent dashboard | Pass (minor) | Low | Fixed | Field-agent wording is about visits.
TC-29 | Site visits | Field agent | Cancel a visit with no reason | Fail | High | Fixed | Reason required; cancel is manager-only.
TC-30 | Site visits | Field agent | Status choices | Fail | Medium | Fixed | Field agents see only their 4 allowed statuses.
TC-31 | PWA | Anyone | Install files | Pass |  | Pass
TC-32 | PWA | Anyone | Install banner | Not tested |  | Not tested
TC-33 | Automated | — | Unit + DB flow tests | Pass |  | Pass
TC-34 | Performance | Anyone | Speed of actions on dev server | Bug | Medium | Mitigated | Spinners everywhere; dev-server slowness is first-time compiling (production is faster).